## Slide 1: CSULB CS 343 Week 12: Risk Management & Project Estimation
Fall 2026 - Risk Matrix, Monte Carlo Simulation

## Slide 2
Learning Objectives
What you will achieve today
By the end of this session, you will be able to:
• Identify technical, schedule, and resource risks
• Build a risk matrix (probability vs impact)
• Apply estimation techniques (PERT, story points)
• Run a simple Monte Carlo simulation for delivery dates
• Present risk mitigation plans to stakeholders

## Slide 3
What is Risk Management?
Identifying and preparing for the unexpected
• Risk = something that MIGHT happen and would cause problems
• Types of risks:
• Technical: new tech, integration challenges
• Schedule: overly optimistic timelines
• Resource: key person leaves, budget cuts
• External: regulations, market changes
• Risk management steps:
1. Identify risks
2. Assess probability and impact
3. Plan mitigation strategies
4. Monitor and update

## Slide 4
The Risk Matrix
Visualizing risk priorities
• Matrix axes: Probability (Low/Med/High) vs Impact (Low/Med/High)
• Zones:
• Red: high probability + high impact (mitigate immediately)
• Yellow: medium (monitor closely)
• Green: low (accept or ignore)
• Example: 'Server outage' = Low probability, High impact
• Example: 'Third-party API changes' = Med probability, Med impact
• Update the matrix weekly throughout the project

## Slide 5
Estimation Techniques
PERT, three-point, and story points
• PERT (Program Evaluation Review Technique):
• Optimistic (O), Most Likely (M), Pessimistic (P)
• Expected time = (O + 4M + P) / 6
• Example:
• O = 3 days, M = 5 days, P = 13 days
• Expected = (3 + 20 + 13) / 6 = 6 days
• Story points (from Week 11): relative estimation
• Always add buffer: estimates are wrong by nature

## Slide 6
Monte Carlo Simulation
Predicting delivery dates with probability
• Monte Carlo: simulate thousands of possible outcomes
• How it works:
1. For each task: define min, max, most likely duration
2. Randomly pick a duration for each task
3. Sum to get total project duration
4. Repeat 10,000 times
5. Analyze distribution of results
• Output: '50th percentile = 45 days, 85th percentile = 55 days'
• Tools: Python script, Excel, Risk management software

## Slide 7
Building a Simple Monte Carlo in Python
Hands-on example
• Sample code structure:
import random
tasks = [{'min': 2, 'max': 5}, ...]
results = []
for _ in range(10000):
total = sum(random.triangular(t['min'], t['max'], t['mode']) for t in tasks)
results.append(total)
• Plot histogram of results
• Find percentiles with numpy or manual sorting
• Present: 'We have an 85% chance of finishing by June 1'

## Slide 8
AI Boost: Risk Generation & Simulation
AI-assisted risk analysis
• Prompt: I'm building a social media app. Identify 7 major risks for my project.
• AI generates risks with probability and impact ratings
• Prompt: Build a Monte Carlo simulation script in Python for my project tasks
• AI outputs boilerplate code - customize the inputs
• Prompt: Summarize these risks for an executive presentation
• AI generates a concise risk matrix report
• Remember: AI identifies common risks; domain-specific ones need human insight

## Slide 9
Soft Skills: Risk Communication
Presenting to executives
• Activity: Prepare a 2-minute risk briefing
• Assume you're presenting to the CEO/CTO
• Structure:
1. Top 3 risks (name + impact)
2. Mitigation plan for each
3. Recommendation (approve plan, accept risk, or change scope)
• Tips:
• No jargon: 'technical debt' -> 'we need to refactor to add features faster'
• Be concise: executives have limited time
• Be honest: don't sugarcoat bad news

## Slide 10
Summary & Looking Ahead
Week 12 Recap
• Risk management: identify -> assess -> mitigate -> monitor
• Risk matrix: probability vs impact visualizes priorities
• PERT and three-point estimation handle uncertainty
• Monte Carlo simulation predicts delivery dates with probability
• AI helps generate risks and build simulation code
• Communicate risks clearly to stakeholders
• Next week: Configuration Management & Version Control
• Assignment: Risk register + Monte Carlo simulation